# Development guidance for Contractors

## Version 1.5 – 26/02/2025

The RFT includes the Hold Point: Prior to establishment and commencement of work on and off site the contractor must submit:

(a)	The Project Quality Plan, and;

(b)	Documented procedures relevant to the Contract.

As defined in the RFT a Project Quality Plan provides an overview of how the work under the Contract will be performed and controlled and Procedures are a documented method for undertaking a certain activity, incorporating a clear allocation of the responsibilities implementation, these can be system procedure, i.e., one relating to the operation or maintenance of the quality system; or a technical procedure, i.e., one describing a works or services related activity.

This document is to be used as an assessment tool for DLI and read in conjunction with the Project Quality Plan. The Contract, RFT and specifications must be referred to in conjunction with these tools as Project Specific Requirements detailed MUST be met.

Please note that the Conditions of Contract (NPWC) Clause 15.3 states that where the contract requires the Contractor to comply with any standard, that standard shall, unless otherwise specified, be that which is current at the closing date for the Request for Tenders. As such PQP will be reviewed in line with AS/NZS ISO9001 Quality Management System – Requirements.

| Abbreviations used in this guidance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PQP | Project Quality Plan |  |  |  |  |
| ISO9001 | AS/NZS ISO9001:2015 Quality Management System - Requirements |  | QMS | Quality Management System |  |
| QMR | Quality Management Representative |  | PM | Project Manager/s |  |
| NPWC | National Public Works Council Conditions of Contract |  | RFT | Request for Tender |  |
| PCWS | Period Contract Works and Services Conditions of Contract |  | RS | Response Schedule |  |
| OFI | Opportunity for Improvement – suggested change only |  | DLI | Department of Logistics and Infrastructure |  |
| Resources - LINKS |  |  |  |  |  |
| Contract Conditions of contract ¦ NT.GOV.AU |  | Compliance.DLI@nt.gov.au |  |  | DLI Specifications Technical specifications ¦ Department of Infrastructure, Planning and Logistics |

| Item |  | Contractual Requirement | ISO9001 Reference | GUIDANCE |
| --- | --- | --- | --- | --- |
|  |  | Project Quality Plan requirements – Quality Assurance Section of the RFT |  |  |
| 1.1 | Management Responsibility | Project Quality Plan: Minimum Requirements Clause (a) | N/A | The PQP must describe the organisational structure for the management of the project with details of the specific responsibilities and authorities of key personnel. These specific responsibilities and authorities must be related to Quality Management on the Project. This may include an organisation chart or similar. |
| 1.2 | Management System Review | Project Quality Plan: Minimum Requirements Clause (a) Quality Assurance Requirements: During the Contract- Hold Point | N/A | The PQP must detail the process to ensure that the Quality System, including the Plan, is reviewed continuously during the course of the Contact. The process must include a Hold Point for the submission of proposed amendments of the Quality System and Plan to the Superintendent for permission to use. |
| 1.3 | Quality Objectives | Project Quality Plan: Minimum Requirements Clause (b) | ISO9001 6.2 | The PQP must include quality objectives relevant to the functions and processes of the Project. The quality objectives must: a) be consistent with the quality policy; b) be measurable; c) take into account applicable requirements, and; d) be relevant to conformity of products and services and to enhancement of customer satisfaction. |
| 1.4 | Quality Management Representative (QMR) | Project Quality Plan: Minimum Requirements Clause (c) | N/A | The PQP must name the proposed Quality Management Representative (QMR) and include details of qualifications and experience. The QMR's responsibilities and authority to resolve quality matters must also be detailed. |
| 1.5 | Technical Procedures and Inspection and Test Plans (ITP's) | Quality Assurance Requirements: During the Contract – Hold Point Project Quality Plan: Minimum Requirements, Clause (d) Quality System Requirements: Process Control Quality System Requirements: Superintendents Quality Audits | ISO9001 8.5.1 | The PQP must have a register of Technical Procedures and Inspection and Test Plans (ITP's) applicable to the contract as per the Quality System Requirements Clause of this Contract. The register must include: - title; - identifier (if applicable), and; - revision status. Technical Procedures (a procedure describing a works or services related activity) must be included as required by the RFT Quality System Requirements - Process Control clause. A sample ITP must be provided. It must include the following information: - date; - product concerned; - name of sub-contractor, if applicable; - when sub-contractors' ITP's are required, verification of their compliance with the specified requirements; - where each inspection and test point is located in the process; - who carries out the inspection or test; - characteristics to be tested; - method of inspection or test; - specified acceptance criteria; - Hold Points and Witness Points; - where lots or batches will be used; - form of record of results; - frequency and timing of the test; and - details of what is to be inspected. Technical Procedures and ITP’s may be combined as one document provided that meet all the requirements of each. As per the Quality Assurance Requirements, During the Contract – Hold Point, ITP’s (other than the sample) and Technical Procedures may not be available at time of the assessment depending on the construction program and the number of working days prior to the activity beginning on site the contractor has been allowed in the RFT. |
| 1.6 | System Procedure Register | Project Quality Plan: Minimum Requirements Clause (e) | ISO9001 | The PQP must have a register of System Procedures applicable to the contract as per the Quality System Requirements Clause of this Contract. The register must include: - title; - identifier (if applicable), and; - revision status. System Procedures that may be required, depending on the contract include: - Contract Review; - Design Control; - Document and Data Control; - Purchasing; - Control of Customer Supplied Product; - Product Identification and Traceability; - Process Control; - Control of Inspection Measuring and Test Equipment; - Inspection and Test Status; - Control of Nonconforming Product; - Corrective and Preventative Action; - Handling, Storage, Packaging, Preservation and Delivery; - Control of Quality Records; - Internal Quality Audits; - Training and; - Servicing. System Procedures may be titled at the discretion of the company, but the contents must meet the requirements as specified in the Quality System Requirements Clause of the Contract. |
| 1.7 | The method of notification of all off-site manufacturing and testing, including materials testing. | Project Quality Plan: Minimum Requirements Clause (f) |  | When offsite manufacturing is within the scope of the project the PQP must include the method of notification of all off-site manufacturing and testing, including materials testing |
| 1.8 | Audit Schedule | Project Quality Plan: Minimum Requirements Clause (g) Quality System Requirements: Internal Quality Audits | ISO9001 9.2.2 | The PQP must include a schedule of external and internal quality audits planned during the Contract period. The audit schedule must take into consideration the importance of the processes concerned and include: - frequency; - methods; - responsibilities; - planning requirements, and; - reporting. If required by RFT Quality System Requirements clause – Internal Quality Audits: The schedule must include internal quality audits at least every four weeks with the first within two weeks of the commencement of work. |